## 📊 Executive Summary (hidden)
WOW GENIE — PHP → NestJS + Next.js Migration Analysis
Executive Summary ¦ June 2026
Total PHP Files Analyzed | Active Core Files | Identified APIs to Build | Common Reusable Functions | Duplicate/Backup Files | Migration Complexity
837 | 354 | 78 | 42 | 483 | HIGH
🎯 Migration Strategy — Strangler Fig Pattern
Phase | Name | Duration | Approach | Key Deliverable | Status
Phase 1 | Foundation & Setup | 2 Weeks | Setup NestJS monorepo + Next.js 14 App Router project; configure DB connections, auth JWT | Project skeleton, CI/CD pipeline, DB TypeORM entities | 🔲 Planned
Phase 2 | Auth & User Module | 2 Weeks | Migrate session-based PHP auth → JWT + Role Guards in NestJS; replicate PHP session role arrays as Guards | AuthModule, UserModule, RoleGuard, Next.js login page | 🔲 Planned
Phase 3 | Core Offer APIs | 4 Weeks | Convert create/edit/save offer PHP pages → NestJS REST APIs; Next.js multi-step forms | OfferModule (CRUD + validation), wizard forms | 🔲 Planned
Phase 4 | Approval Workflow | 3 Weeks | Convert approval chain (WS→RWM→CM→VPB2B→DA→DF→RF→RVP) to NestJS state machine | ApprovalModule, notification service | 🔲 Planned
Phase 5 | Financial Calculations | 3 Weeks | Port GM/PPM/IRR/NPV calculation PHP logic → NestJS service; validate outputs match PHP exactly | CalculationService, FinancialsModule, test suite | 🔲 Planned
Phase 6 | Reports & Exports | 3 Weeks | Port PHPExcel reports → ExcelJS/PDFKit in NestJS; cron jobs via NestJS scheduler | ReportsModule, PDFService, CronJobs | 🔲 Planned
Phase 7 | External Integrations | 2 Weeks | Port SFTP upload, Mailer (PHPMailer → Nodemailer), FTP discount generation | IntegrationsModule, MailService, SFTPService | 🔲 Planned
Phase 8 | QA & Cutover | 2 Weeks | Full regression, parallel run, data migration scripts, DNS cutover | Go-live readiness, migration docs | 🔲 Planned
🛠 Technology Stack — New Architecture
Layer | Old (PHP) | New (NestJS/Next) | Library/Tool | Reason | Effort
Backend Framework | Core PHP 7.x | NestJS 10 (Node.js) | TypeScript + Express | Type safety, decorators, modular architecture, built-in DI
Frontend | PHP HTML templates (embedded) | Next.js 14 (App Router) | React 18 + TypeScript | SSR/SSG, file-based routing, React Server Components
Database Access | mysqli_ raw queries | TypeORM 0.3 | TypeORM + MySQL/PostgreSQL | ORM with migrations, relations, typed entities
Authentication | PHP $_SESSION + session_start() | JWT + Passport.js | passport-jwt, @nestjs/jwt | Stateless auth, role-based guards, refresh tokens
Authorization / Roles | Hardcoded $login_array role arrays | NestJS Guards + Decorators | @Roles() decorator + RolesGuard | Clean separation, extensible RBAC
Email / Mailer | PHPMailer class.phpmailer.php | Nodemailer + @nestjs-modules/mailer | Nodemailer + Handlebars templates | Async queued emails, HTML templates
Excel Generation | PHPExcel / PhpSpreadsheet | ExcelJS | exceljs npm package | Full Excel feature parity, streaming large files
PDF Generation | TCPDF / custom casn_report_pdf | PDFKit / Puppeteer | pdfkit or @nestjs/puppeteer | Pixel-perfect PDFs from HTML templates
SFTP / FTP | phpseclib + SSH2 | ssh2-sftp-client | ssh2-sftp-client npm | Async SFTP, retry logic
Cron Jobs | Linux crontab calling PHP files | NestJS Scheduler | @nestjs/schedule @Cron() | In-process scheduling, testable, manageable
File Storage | Local filesystem + zip() | AWS S3 / local + archiver | archiver npm for ZIP | Scalable, CDN-ready
State Management | PHP $_SESSION | Redux Toolkit (client) + JWT (server) | RTK + react-query | Predictable state, server cache sync
Forms | HTML forms + PHP POST | React Hook Form + Zod | react-hook-form + zod | Type-safe validation, multi-step wizard support
API Communication | Direct PHP page calls / AJAX | REST API (NestJS) + Axios/fetch | axios, @tanstack/react-query | Typed API client, caching, optimistic updates
Testing | None | Jest + Supertest + RTL | jest, supertest, @testing-library/react | Unit + integration + E2E coverage

## 🔄 Repeated Functions
COMMON & REPEATED PHP FUNCTIONS — Migration Map
Functions found across multiple files that should become shared services in NestJS
Sr. | PHP Pattern / Snippet | Found In (Files) | Frequency | Category | NestJS Service / Method | Module | Priority | Notes
1 | session_start() + $_SESSION['usercode_s'] + $_SESSION['user_rolecode_s'] | save_offer, approve_offer, publish_offer, cancel_offer, recall.php, ALL 50+ files | 50+ | Authentication | AuthService.validateSession(req) → JWT Guard @UseGuards(JwtAuthGuard) | AuthModule | 🔴 Critical | Every PHP file starts with this block. Replace with NestJS JWT Guard applied globally or per-route.
2 | require './includes/config.inc.php' + DB connect via mysqli | Nearly ALL PHP files | 100+ | Database/Config | TypeORM DataSource configured in AppModule; inject repositories via @InjectRepository() | AppModule / TypeORM | 🔴 Critical | Central DB config → TypeORM ormconfig / datasource.ts; env vars via @nestjs/config
3 | $login_array = array('WS'=>'WS','RWM'=>'RWM','CM'=>...); role chain arrays | approve_offer, recall, publish_offer, cancel_approval, 20+ files | 20+ | Authorization / RBAC | ROLES enum + @Roles('WS','RWM') + RolesGuard; ApprovalChain config constant | AuthModule / PolicyModule | 🔴 Critical | Port PHP role arrays to NestJS enum. Approval chain config in DB or constant map.
4 | core_decrypt($_GET['offerID']) / base64_decode() | financials, data, recall, publish_offer, 30+ files | 30+ | Security / Utility | CryptoService.decrypt(id) called in pipe or guard; use NestJS ParseIntPipe or custom pipe | CommonModule / CryptoService | 🔴 Critical | Centralize decryption. Consider migrating to UUID instead of encrypted integer IDs.
5 | mysqli_query($GLOBALS['___mysqli_ston'], $sql) or die() | ALL files | 200+ | Database | Repository pattern: this.offerRepo.findOne({where:{id}}); TypeORM QueryBuilder for complex queries | All Modules | 🔴 Critical | Raw SQL → TypeORM entities/repositories. Keep raw QueryBuilder for complex joins.
6 | mysqli_fetch_array / mysqli_fetch_assoc / mysqli_num_rows | ALL files | 200+ | Database | Async/await repository methods: find, findOne, findAndCount, save, update, delete | All Modules | 🔴 Critical | Replace all mysqli fetch patterns with TypeORM async repository calls.
7 | unserialize($row['sku_text']) / serialize($data) | recall, cancel_offer, publish_offer, approve_offer, output_lc, 20+ files | 20+ | Data Serialization | Store as JSON column in MySQL (JSON type); use JSON.parse/stringify in NestJS. Migrate existing serialized data. | OfferModule / SKUModule | 🔴 Critical | PHP serialize → JSON. Write one-time migration script to convert DB column from serialize → JSON.
8 | require('class.phpmailer.php') + $mail->AddAddress() + $mail->Send() | recall, publish_offer, cancel_approval, wbc_approval_pipeline_automailer, 15+ files | 15+ | Email / Notifications | MailService.sendNotification(dto) using @nestjs-modules/mailer + Handlebars templates | MailModule | 🔴 Critical | Centralise all email sending into MailService. Templates in HBS files. Queue with Bull.
9 | moneyformatindia(round($value, 2)) — Indian number formatting | recall, output_lc, financials, 15+ files | 15+ | Utilities / Formatting | formatters.ts: export function moneyFormatIndia(value: number): string | CommonModule / utils | 🟡 Medium | Pure utility function. Create shared utils/formatters.ts used by both FE and BE.
10 | salesTaxorGST_on_date($date, $rate) — Tax type based on date | financials, data, output_lc, 10+ files | 10+ | Business Logic / Tax | TaxService.getTaxLabel(date: Date, rate: number): string (GST/Sales Tax cutover 01-Jul-2017) | FinanceModule / TaxService | 🟡 Medium | Centralize GST/Sales Tax date-based logic. Test boundary: 01-Jul-2017.
11 | Date calculations: new DateTime(); ->modify('+12 months'); ->modify('-1 day'); year1..year6 computation | financials, calculation, data_calc, offer_list, 10+ files | 10+ | Business Logic / Finance | DateUtilService.computeContractYears(startDate, endDate): ContractYears | FinanceModule / DateUtils | 🟡 Medium | Contract year splitting logic repeated in financials.php, calculation.php, data_calc.php. Extract to service.
12 | Cost Inflation Rate loop: Cost_Inflation_Rate_constant[i] = prev * (1 + rate/100) | financials.php, calculation.php, financials_cs, financials_ts, financials_vs | 5+ | Financial Calculation | FinancialCalcService.computeInflationRates(rates: number[], startYear, endYear): number[] | FinanceModule | 🔴 Critical | Core NPV/IRR input. Exact replication required. Add unit tests comparing PHP vs NestJS outputs.
13 | IRR / NPV calculation loops (investmentArray, cashflowArray) | financials.php, financials_cs, financials_ts, output_lc, calculation | 5+ | Financial Calculation | FinancialCalcService.calculateIRR(cashflows: number[]): number; calculateNPV(rate, cashflows): number | FinanceModule | 🔴 Critical | Financial math. Use financial.js npm library or port PHP bisection method. Validate against PHP outputs.
14 | GM Pool / GM P/L calculation: (listprice - cogs - discount - foc - investment) * volume | financials, output_lc, calculation, offer_list | 5+ | Financial Calculation | FinancialCalcService.calculateGMPool(params: GMCalcDto): GMResult | FinanceModule | 🔴 Critical | Business-critical GM calculation. Extract all formula variants (CS/TS/VS/normal) into one parameterized service.
15 | PHPExcel style blocks: $yellow/$blue/$borders arrays, setCellValue, applyFromArray | calculation, offer_list, all_report, history_ajax_download, 20+ files | 20+ | Report Generation | ExcelReportService using ExcelJS: workbook.addWorksheet(); ws.addRow(); ws.getColumn().style() | ReportsModule / ExcelService | 🟡 Medium | Replace PHPExcel with ExcelJS. Create base ExcelTemplate class with common styles.
16 | PDF generation: require_once 'tcpdf...' / casn_report_pdf blocks, HTML table → PDF | casn_report_pdf, pitstop_report_pdf, ws_report_pdf, 8+ files | 8+ | Report Generation | PDFService using Puppeteer or PDFKit. React templates rendered server-side → PDF. | ReportsModule / PDFService | 🟡 Medium | Use Puppeteer (HTML→PDF) or PDFKit for programmatic generation. Agree on one approach.
17 | SFTP upload: $sftp->login() + $sftp->put(remote, local) | sku_discount_generation_ftp_upload, tvd_ftp_keta, stfp_biztest | 5+ | Integration / FTP | SFTPService using ssh2-sftp-client: sftp.put(localPath, remotePath) | IntegrationsModule / SFTPService | 🟡 Medium | Single SFTP service. Credentials via environment variables, not hardcoded.
18 | $sessionRole == 'WS' ¦¦ $sessionRole == 'ASM' ¦¦ $sessionRole == 'KAS' checks | publish_offer, create_offer_s1, edit_offer_s1, 20+ files | 20+ | Authorization | @Roles(Role.WS, Role.ASM, Role.KAS) + RolesGuard at controller level | AuthModule | 🔴 Critical | All inline role checks → centralized Guard + Role enum.
19 | Duplicate offer validation: check matching customer_code/parent_id pairs in loops | save_offer.php (lines 86-100+), save_offer_pitstop, save_offer_extended | 3+ | Business Logic / Validation | OfferValidationService.checkDuplicatePIDs(pids: PidDto[]): ValidationResult | OfferModule / ValidationService | 🟡 Medium | Port nested for-loop duplicate check. Can use Set for O(n) vs O(n²).
20 | adminmail() function call — get admin email from DB | recall, cancel_approval, wbc_approval_pipeline_automailer, 8+ files | 8+ | Utilities / Config | ConfigService.get('WEB_ADMIN_EMAIL') or SettingsService.getAdminEmail(): Promise<string> | CommonModule / SettingsService | 🟡 Medium | Move admin config to .env or DB settings table.
21 | ini_set('memory_limit', '1024M') at top of heavy report files | publish_offer, output_lc, create_offer_output_lc_view, 10+ files | 10+ | Performance / Config | Node.js --max-old-space-size=2048 flag; use streaming for large Excel/PDF exports | DevOps / Config | 🟡 Medium | Handle via Node.js process flag and streaming patterns, not per-request config.
22 | ob_start() / ob_end_flush() — output buffering for PDF/Excel | casn_report_pdf, output_lc_excel, ajax_download_excel_report, 10+ files | 10+ | Output Streaming | NestJS StreamableFile or res.setHeader() + stream pipe; ExcelJS write to stream | ReportsModule | 🟡 Medium | Replace PHP output buffering with Node.js readable streams piped to HTTP response.
23 | JSON echo for AJAX: echo json_encode(['success'=>true, 'data'=>...]); exit; | ajax_sku_code, customer_set_ajax, customer_get_ajax, offer_pipeline_s3_ajax, 15+ files | 15+ | API Response | NestJS controller returning typed DTO; interceptors format {success, data, message} | All Modules | 🔴 Critical | All AJAX endpoints become proper REST endpoints with consistent response envelope.
24 | Pagination: LIMIT $start, $per_page in SQL queries | offer_pipeline_s2, nav_pipeline, all_report, 10+ files | 10+ | Database / Pagination | TypeORM findAndCount + PageOptionsDto: {page, limit, order}; NestJS Swagger pagination | All Modules | 🟡 Medium | Standardize pagination: {page, limit} query params → {data, total, page, lastPage}.
25 | File upload: move_uploaded_file($_FILES['file']['tmp_name'], $dest) | upload_additional_docs, pricing_upload_itemmaster, import_pid_details, 8+ files | 8+ | File Handling | NestJS @UploadedFile() + MulterModule; FileInterceptor('file'); store in S3 or /uploads | CommonModule / FileService | 🟡 Medium | Use NestJS Multer integration. Validate file type/size. Consider S3 for production.
26 | ZIP archive: ZipArchive + addFile() / zip_close() | contract_details_zip, offer_closure_zip, customer_data_zip, 10+ files | 10+ | File Handling | ArchiveService using 'archiver' npm: archive.append(stream, {name}); archive.finalize() | CommonModule / ArchiveService | 🟡 Medium | Single ArchiveService. Use archiver npm. Stream directly to HTTP response.
27 | DOFA (Delegation of Financial Authority) level logic: $getLevel, $levelRole array | approve_offer, cancel_approval, recall, 5+ files | 5+ | Business Logic / Workflow | ApprovalWorkflowService.getNextApprover(offer, currentLevel): ApprovalStep | ApprovalModule | 🔴 Critical | DOFA is a core workflow. Model as state machine (e.g., XState or custom). Each level = a state.
28 | Offer status codes: 'D'=Draft, 'P'=Pending, 'A'=Approved, 'E'=Expired, 'C'=Cancelled, 'I'=Inactive | approve_offer, cancel_offer, publish_offer, offer_pipeline_s2, ALL | 50+ | Domain Constants | enum OfferStatus { Draft='D', Pending='P', Approved='A', Expired='E', Cancelled='C', Inactive='I' } | Domain / OfferModule | 🔴 Critical | Create TypeScript enum. Use in all DTOs, entities, guards. Add state transition validation.
29 | WBC / Pitstop / IWS / TataPCD variant logic: if($is_pitstop=='Y') ... else ... | create_offer_s1_pitstop, edit_offer_s1_pitstop, create_offer_s2_pitstop, 30+ files | 30+ | Business Logic / Multi-Variant | Use offer_type field (enum: STANDARD, PITSTOP, IWS, TATAPCD); strategy pattern per type | OfferModule / StrategyPattern | 🔴 Critical | Biggest duplication source. Apply Strategy pattern: OfferStrategy interface + 4 implementations.
30 | Amendment / Extended offer flow: create_amendment_offer_s1/s2/s3 | create_amendment_offer_*, create_extended_offer_*, edit_extended_offer_* | 15+ | Business Logic / Offer Types | OfferType enum: ORIGINAL, AMENDMENT, EXTENDED; parent_offer_id FK for lineage | OfferModule | 🔴 Critical | Model offer hierarchy with parent_offer_id. Common base, variant-specific fields.
31 | SKU discount FTP generation daily cron | sku_discount_generation_ftp_upload_daily, sku_discount_daily_live, 8+ variants | 8+ | Cron / Integration | @Cron('0 0 * * *') in SkuDiscountCronService; SkuDiscountService.generateAndUpload() | CronModule / IntegrationsModule | 🟡 Medium | Single cron service. Parameterize for different channels (NCIT, Ford, daily, manual).
32 | Reminder mailer crons: reminder_mail_publish, reminder_mail_contract_extension | reminder_mail_publish, reminder_mail_contract_extension, reminder_mail_pending_3days | 6+ | Cron / Notifications | @Cron('0 8 * * *') in ReminderCronService; MailService.sendReminder(offerIds, templateId) | CronModule / MailModule | 🟡 Medium | Consolidate all reminder crons into one service with template selection.
33 | Publish date validation: check effective_end_date, start_date, overlap detection | save_offer, publish_offer, extend_offer, 8+ files | 8+ | Business Logic / Validation | OfferValidationService.validateDates(dto: DateRangeDto): ValidationError[] | OfferModule / ValidationService | 🟡 Medium | Centralized date validation. Use date-fns for reliable date arithmetic.
34 | KAS / SAM / ASM / WS / WSM role-based form field visibility toggles | publish_offer, create_offer_s1, edit_offer_s1, commercial_input_view, 15+ files | 15+ | UI / Authorization | useRolePermissions() React hook; API endpoint GET /permissions/form-fields | AuthModule + Next.js Hook | 🟡 Medium | Dynamic form field visibility based on role. Config-driven rather than if/else PHP.
35 | Keris integration: keris_submition_form, keris_updation_form, keris_view_submit | keris_submition_form, keris_updation_form, keris_view_submit, 5+ files | 5+ | Integration / External | KerisIntegrationService: submit(), update(), fetchStatus() calling Keris API | IntegrationsModule / KerisService | 🟡 Medium | Isolate Keris integration into dedicated service. Add retry + circuit breaker.
36 | Customer data fetch AJAX: customer_get_ajax, customer_pitstop_get_ajax | customer_get_ajax, customer_pitstop_get_ajax, customer_set_ajax | 4+ | API / Customer | GET /customers/:id/offer-data → CustomerController.getForOffer(offerId: string) | CustomerModule | 🟡 Medium | Unify standard/pitstop customer AJAX into single parameterized endpoint.
37 | PID mapping validation: pidAdd, pidAddDirect, import_pid_details | pidAdd, pidAddDirect, import_pid_details, pid_mapping | 4+ | Business Logic / PID | PIDService.validate(pid), PIDService.bulkImport(file), PIDService.mapToOffer(offerId, pids) | PIDModule | 🟡 Medium | PID = customer parent ID. Separate CRUD module with validation.
38 | Discount calculation per SKU: sku_price, sku_discount, check_sku_item_value | sku_price, sku_discount, check_sku_item_value, ajax_sku_code | 8+ | Business Logic / Pricing | SKUDiscountService.calculateDiscount(skuCode, volume, listPrice): DiscountResult | SKUModule / PricingModule | 🟡 Medium | Extract per-SKU pricing logic into dedicated service with typed inputs/outputs.
39 | Credit level pending report queries | bp_credit_level_pending_report, credit_level_pending_days, ppm_level_pending_days | 4+ | Reporting / Business | GET /reports/credit-pending → ReportsController; query via TypeORM with date filters | ReportsModule | 🟢 Low | Standard report endpoint with query params filter.
40 | WBC number generation / offer code assignment | create_offer_s2, create_offer_s2_pitstop, save_offer, 5+ files | 5+ | Business Logic / ID Generation | OfferService.generateWBCNumber(params): string; atomic counter or DB sequence | OfferModule | 🔴 Critical | Use DB auto-increment + prefix, or UUID v4 with code formatter. Needs atomic transaction.
41 | Publishing approval email with offer HTML table | publish_offer, recall, cancel_approval, wbc_approval_pipeline_automailer | 5+ | Email / Templating | MailService.sendApprovalEmail(offer, level, action): void with Handlebars template | MailModule | 🟡 Medium | One HBS template per event type. Reuse offer summary partial template.
42 | Volume plan data: volume_plan, volume_plan_2, wbc_active_pid_wise_volume_report | volume_plan, volume_plan_2, wbc_active_pid_wise | 3+ | Business Logic / Volume | VolumePlanService.getByOffer(offerId), VolumePlanService.aggregate() | OfferModule / VolumePlanModule | 🟢 Low | Separate volume plan sub-module.

## 🌐 API Inventory
NESTJS API ENDPOINT INVENTORY
All REST API endpoints to be built — mapped from PHP files
Sr. | HTTP Method | Endpoint | PHP Source File(s) | Controller | Service Method | Module | Auth Required | Roles | Priority
1 | POST | /auth/login | index.php (login section) | AuthController | AuthService.login(dto) | AuthModule | No | Public | 🔴 Critical
2 | POST | /auth/refresh | PHP Session refresh logic | AuthController | AuthService.refreshToken(dto) | AuthModule | Yes (Refresh) | All | 🔴 Critical
3 | POST | /auth/logout | PHP session_destroy() | AuthController | AuthService.logout(userId) | AuthModule | Yes | All | 🔴 Critical
4 | GET | /auth/me | PHP session check blocks | AuthController | AuthService.getProfile(userId) | AuthModule | Yes | All | 🔴 Critical
5 | POST | /auth/send-password | send_mail.php | AuthController | AuthService.sendPassword(email) | AuthModule | No | Public | 🟡 Medium
6 | GET | /offers | offer_pipeline_s2.php, nav_pipeline.php | OfferController | OfferService.findAll(filters, page) | OfferModule | Yes | WS,ASM,KAS,SAM,RWM,WSM,All Roles | 🔴 Critical
7 | GET | /offers/:id | create_offer_output_lc_view.php, edit_offer_output_lc_view.php | OfferController | OfferService.findOne(id) | OfferModule | Yes | All | 🔴 Critical
8 | POST | /offers | create_offer_s1.php + create_offer_s2.php + create_offer_s3.php | OfferController | OfferService.create(dto) | OfferModule | Yes | WS,ASM,KAS,SAM | 🔴 Critical
9 | PUT | /offers/:id | edit_offer_s1.php + edit_offer_s2.php + edit_offer_s3.php | OfferController | OfferService.update(id, dto) | OfferModule | Yes | WS,ASM,KAS,SAM | 🔴 Critical
10 | DELETE | /offers/:id | delete_offer.php | OfferController | OfferService.softDelete(id) | OfferModule | Yes | WS,ASM | 🟡 Medium
11 | POST | /offers/:id/save | save_offer.php, save_offer_pitstop.php, save_offer_extended.php | OfferController | OfferService.save(id, sessionData) | OfferModule | Yes | WS,ASM,KAS,SAM | 🔴 Critical
12 | POST | /offers/:id/publish | publish_offer.php (2639 lines) | OfferController | OfferService.publish(id, dto) | OfferModule | Yes | WS,ASM,KAS,SAM | 🔴 Critical
13 | POST | /offers/:id/approve | approve_offer.php (2485 lines) | ApprovalController | ApprovalService.approve(id, userId, level) | ApprovalModule | Yes | RWM,CM,VPB2B,DA,DF,RF,RVP,GMWBC | 🔴 Critical
14 | POST | /offers/:id/reject | approve_offer.php rejection section | ApprovalController | ApprovalService.reject(id, userId, reason) | ApprovalModule | Yes | All Approvers | 🔴 Critical
15 | POST | /offers/:id/recall | recall.php | OfferController | OfferService.recall(id, userId) | OfferModule | Yes | WS,ASM | 🔴 Critical
16 | POST | /offers/:id/cancel | cancel_offer.php | OfferController | OfferService.cancel(id, dto) | OfferModule | Yes | WS,ASM,WSM | 🔴 Critical
17 | POST | /offers/:id/extend | extend_offer.php, extend_offer_iws.php | OfferController | OfferService.extend(id, newEndDate) | OfferModule | Yes | WS,ASM | 🟡 Medium
18 | POST | /offers/:id/amend | create_amendment_offer_s1/s2/s3.php | OfferController | OfferService.createAmendment(id, dto) | OfferModule | Yes | WS,ASM | 🟡 Medium
19 | GET | /approvals/pipeline | offer_pipeline_s1/s2/s3.php | ApprovalController | ApprovalService.getPipeline(userId, role, filters) | ApprovalModule | Yes | All Approvers | 🔴 Critical
20 | GET | /approvals/:id/history | offer_pipeline_s3.php timeline | ApprovalController | ApprovalService.getHistory(offerId) | ApprovalModule | Yes | All | 🟡 Medium
21 | POST | /approvals/cancel-approval | cancel_approval.php, cancel_approval_reactivation.php | ApprovalController | ApprovalService.cancelApproval(id) | ApprovalModule | Yes | WSM,CM+ | 🟡 Medium
22 | POST | /approvals/rtm | RTM_approval.php | ApprovalController | ApprovalService.submitRTM(offerId, data) | ApprovalModule | Yes | WSM | 🟡 Medium
23 | GET | /financials/:offerId | financials.php, financials_cs/ts/vs.php | FinancialController | FinancialService.compute(offerId) | FinanceModule | Yes | All | 🔴 Critical
24 | GET | /financials/:offerId/irr-npv | output_lc.php IRR/NPV section | FinancialController | FinancialService.getIRRNPV(offerId) | FinanceModule | Yes | All | 🔴 Critical
25 | GET | /financials/:offerId/output-lc | output_lc.php (225KB) | FinancialController | FinancialService.getOutputLC(offerId) | FinanceModule | Yes | All | 🔴 Critical
26 | GET | /financials/input | fin_input.php | FinancialController | FinancialService.getFinancialInput() | FinanceModule | Yes | Admin | 🟡 Medium
27 | POST | /financials/input | fin_input.php POST | FinancialController | FinancialService.updateFinancialInput(dto) | FinanceModule | Yes | Admin | 🟡 Medium
28 | GET | /sku/codes | ajax_sku_code.php | SKUController | SKUService.getCodes(filters) | SKUModule | Yes | WS,ASM+ | 🔴 Critical
29 | POST | /sku/change | change_sku_code.php, change_sku_code_iws.php | SKUController | SKUService.changeCode(dto) | SKUModule | Yes | Admin,WSM | 🟡 Medium
30 | GET | /sku/price | sku_price.php, sku_price_pitstop.php | SKUController | SKUService.getPrice(skuCode, type) | SKUModule | Yes | All | 🟡 Medium
31 | POST | /sku/bulk-change | mapped_sku_change.php, mapped_sku_change_bulk_download.php | SKUController | SKUService.bulkChange(dto) | SKUModule | Yes | Admin | 🟡 Medium
32 | GET | /sku/discount | sku_discount_download.php, sku_discount_download_pitstop.php | SKUController | SKUService.getDiscount(skuCode) | SKUModule | Yes | All | 🟡 Medium
33 | POST | /sku/validate | check_sku_item_value.php | SKUController | SKUService.validate(skuCode, value) | SKUModule | Yes | WS,ASM | 🔴 Critical
34 | GET | /customers/search | customer_get_ajax.php, customer_pitstop_get_ajax.php | CustomerController | CustomerService.search(query, type) | CustomerModule | Yes | WS,ASM+ | 🔴 Critical
35 | POST | /customers/set | customer_set_ajax.php, customer_pitstop_set_ajax.php | CustomerController | CustomerService.associateWithOffer(dto) | CustomerModule | Yes | WS,ASM | 🔴 Critical
36 | GET | /customers/:id/data | customer_data.php | CustomerController | CustomerService.getFullData(id) | CustomerModule | Yes | All | 🟡 Medium
37 | GET | /pid-mapping | pid_mapping.php | PIDController | PIDService.getMapping(filters) | PIDModule | Yes | WS,ASM,WSM | 🟡 Medium
38 | POST | /pid-mapping | pidAdd.php, pidAddDirect.php | PIDController | PIDService.add(dto) | PIDModule | Yes | WS,ASM | 🟡 Medium
39 | POST | /pid-mapping/import | import_pid_details.php | PIDController | PIDService.bulkImport(file) | PIDModule | Yes | Admin | 🟡 Medium
40 | GET | /reports/all-offers | all_report.php | ReportsController | ReportsService.getAllOffers(filters) | ReportsModule | Yes | All | 🟡 Medium
41 | GET | /reports/anp | anp_report.php | ReportsController | ReportsService.getANP(filters) | ReportsModule | Yes | RWM+ | 🟡 Medium
42 | GET | /reports/input-tracker | input_tracker.php | ReportsController | ReportsService.getInputTracker(period) | ReportsModule | Yes | Admin,RWM+ | 🟡 Medium
43 | GET | /reports/credit-pending | bp_credit_level_pending_report.php | ReportsController | ReportsService.getCreditPending() | ReportsModule | Yes | CM+ | 🟡 Medium
44 | GET | /reports/sku-brand-analysis | sku_brand_analysis.php | ReportsController | ReportsService.getSKUBrandAnalysis() | ReportsModule | Yes | RWM+ | 🟢 Low
45 | GET | /reports/pipeline-s2 | offer_pipeline_s2_report.php | ReportsController | ReportsService.getPipelineS2(filters) | ReportsModule | Yes | All Approvers | 🟡 Medium
46 | GET | /downloads/offer-excel/:offerId | ajax_download_excel_report.php, ajax_download_excel_report_iws.php | DownloadsController | DownloadsService.generateOfferExcel(offerId) | ReportsModule | Yes | All | 🟡 Medium
47 | GET | /downloads/casn-pdf/:offerId | casn_report_pdf_none_type.php, casn_report_pdf_none_type_onfly.php | DownloadsController | DownloadsService.generateCASNPdf(offerId) | ReportsModule | Yes | All | 🟡 Medium
48 | GET | /downloads/pitstop-pdf/:offerId | pitstop_report_pdf_none_type.php | DownloadsController | DownloadsService.generatePitstopPdf(offerId) | ReportsModule | Yes | All | 🟡 Medium
49 | GET | /downloads/sku-discount-report | sku_discount_download.php | DownloadsController | DownloadsService.getSkuDiscountReport(filters) | ReportsModule | Yes | Admin,RWM+ | 🟡 Medium
50 | GET | /downloads/output-lc-excel/:offerId | output_lc_excel.php | DownloadsController | DownloadsService.getOutputLCExcel(offerId) | ReportsModule | Yes | All | 🟡 Medium
51 | GET | /downloads/all-offers | alloffer_download.php | DownloadsController | DownloadsService.downloadAllOffers(filters) | ReportsModule | Yes | Admin | 🟢 Low
52 | GET | /downloads/bulk-sku | download_bulk_sku.php | DownloadsController | DownloadsService.downloadBulkSKU(type) | ReportsModule | Yes | Admin | 🟢 Low
53 | GET | /downloads/item-master | download_item_master_excel.php | DownloadsController | DownloadsService.downloadItemMaster() | ReportsModule | Yes | Admin | 🟢 Low
54 | GET | /commercial-input/:offerId | commercial_input_view.php | CommercialController | CommercialService.get(offerId) | CommercialModule | Yes | All | 🔴 Critical
55 | POST | /commercial-input/:offerId | commercial_input_view.php POST | CommercialController | CommercialService.save(offerId, dto) | CommercialModule | Yes | WS,ASM | 🔴 Critical
56 | POST | /commercial-input/:offerId/credit | credit_input.php | CommercialController | CommercialService.saveCredit(offerId, dto) | CommercialModule | Yes | WS,ASM,CM | 🟡 Medium
57 | POST | /keris/submit | keris_submition_form.php | KerisController | KerisService.submit(dto) | IntegrationsModule | Yes | WS,ASM | 🟡 Medium
58 | PUT | /keris/update | keris_updation_form.php | KerisController | KerisService.update(dto) | IntegrationsModule | Yes | WS,ASM | 🟡 Medium
59 | GET | /keris/:offerId/status | keris_view_submit.php | KerisController | KerisService.getStatus(offerId) | IntegrationsModule | Yes | All | 🟡 Medium
60 | POST | /notifications/send-approval-mail | wbc_approval_pipeline_automailer.php | NotificationController | NotificationService.sendApprovalMail(dto) | NotificationModule | Yes (Internal) | System | 🟡 Medium
61 | POST | /notifications/reminder | reminder_mail_publish.php, reminder_mail_contract_extension.php | NotificationController | NotificationService.sendReminder(type, filters) | NotificationModule | Yes (Internal) | System/Admin | 🟡 Medium
62 | POST | /notifications/launch-alert | launch_alert.php, cron_publish_alert_wsm.php | NotificationController | NotificationService.sendLaunchAlert(offerId) | NotificationModule | Yes | Admin | 🟡 Medium
63 | POST | /uploads/documents | upload_additional_docs.php, upload_docs_off_wbc.php | UploadsController | UploadsService.uploadDocument(file, metadata) | CommonModule | Yes | WS,ASM+ | 🟡 Medium
64 | POST | /uploads/item-master | pricing_upload_itemmaster.php, pricing_upload_pitstop_itemmaster.php | UploadsController | UploadsService.uploadItemMaster(file, type) | PricingModule | Yes | Admin | 🟡 Medium
65 | POST | /uploads/jbr | pricing_upload_jbr.php | UploadsController | UploadsService.uploadJBR(file) | PricingModule | Yes | Admin | 🟡 Medium
66 | GET | /offer-closure/:offerId | offer_closure_details.php, offer_closure_sku.php | OfferClosureController | OfferClosureService.get(offerId) | OfferClosureModule | Yes | All | 🟡 Medium
67 | POST | /offer-closure/:offerId/sku | offer_closure_sku.php POST | OfferClosureController | OfferClosureService.saveSkuClosure(dto) | OfferClosureModule | Yes | WS,ASM | 🟡 Medium
68 | POST | /sku-discount/generate | sku_discount_generation_ftp_upload.php | SKUDiscountController | SKUDiscountService.generateManual(params) | SKUModule | Yes | Admin | 🟡 Medium
69 | POST | /sku-discount/ftp-upload | sku_discount_generation_ftp_upload_daily.php | SKUDiscountController | SKUDiscountService.uploadToFTP(params) | SKUModule | Yes | Admin/Cron | 🟡 Medium
70 | GET | /sku-discount/file | sku_discount_file_generation.php | SKUDiscountController | SKUDiscountService.generateFile(filters) | SKUModule | Yes | Admin | 🟡 Medium
71 | POST | /special-price/automation | special_price_automation_direct_customers.php | PricingController | PricingService.automateSpecialPrice(dto) | PricingModule | Yes | Admin | 🟢 Low
72 | GET | /special-price/report | special_price_report dir | PricingController | PricingService.getSpecialPriceReport(filters) | PricingModule | Yes | RWM+ | 🟢 Low
73 | GET | /admin/financial-input | fin_input.php admin section | AdminController | AdminService.getFinancialInput() | AdminModule | Yes | Admin only | 🟡 Medium
74 | POST | /admin/financial-input | fin_input.php save | AdminController | AdminService.saveFinancialInput(dto) | AdminModule | Yes | Admin only | 🟡 Medium
75 | GET | /admin/dofa-config | DOFA.php, dofa_active.php | AdminController | AdminService.getDOFAConfig() | AdminModule | Yes | Admin only | 🟡 Medium
76 | PUT | /admin/dofa-config | DOFA.php | AdminController | AdminService.updateDOFAConfig(dto) | AdminModule | Yes | Admin only | 🟡 Medium
77 | POST | /offers/:id/simulate | edit_offer_simulation_pdf.php, edit_offer_s2_simulation.php | OfferController | OfferService.simulate(id, overrides) | OfferModule | Yes | WS,ASM,WSM | 🟢 Low
78 | POST | /cron/trigger/:jobName | All cron PHP files | CronController | CronService.triggerManually(jobName) | CronModule | Yes | Admin only | 🟢 Low

## 📁 File→Component Map
PHP FILE → NESTJS/NEXTJS COMPONENT MAPPING
Each active PHP file mapped to its NestJS module + Next.js page equivalent
PHP File | File Type | Size (KB) | Complexity | NestJS Component | Next.js Page/Component | Module | Action | Notes
index.php (login) | Page + Logic | 14 | Medium | AuthModule: AuthController, AuthService, JWT Strategy | app/(auth)/login/page.tsx | AuthModule | CONVERT | Main entry. PHP session → JWT. Login form → React Hook Form + Zod
send_mail.php | Utility + Page | 5 | Low | AuthModule: POST /auth/send-password | app/(auth)/forgot-password/page.tsx | AuthModule | CONVERT | Password recovery email. Nodemailer template.
create_offer_s1.php | Page (Step 1) | 58 | High | OfferModule: CreateOfferDto (step1) | app/(offers)/create/step1/page.tsx | OfferModule | CONVERT | Multi-step form Step 1: Customer selection, dates, offer type
create_offer_s2.php | Page + Logic (Step 2) | 159 | Very High | OfferModule: CreateOfferStep2Dto + OfferService.saveStep2() | app/(offers)/create/step2/page.tsx | OfferModule | CONVERT | Step 2: SKU selection, volume, pricing inputs. 159KB → break into components
create_offer_s3.php | Page (Step 3) | 83 | High | OfferModule: OfferService.saveStep3() | app/(offers)/create/step3/page.tsx | OfferModule | CONVERT | Step 3: Confirmation + final adjustments
save_offer.php | AJAX Handler | 61 | Very High | OfferModule: POST /offers → OfferService.create() | Next.js form submission → API | OfferModule | CONVERT→API | Core save logic. Extract validation to OfferValidationService
create_offer_output_lc_view.php | Report Page | 326 | Very High | FinanceModule: GET /financials/:id/output-lc | app/(offers)/[id]/output/page.tsx | FinanceModule | CONVERT | 326KB! Largest file. Split into: OutputHeader, SKUTable, FinancialSummary, Charts components
edit_offer_s1.php | Page (Edit Step 1) | 87 | High | OfferModule: UpdateOfferDto | app/(offers)/[id]/edit/step1/page.tsx | OfferModule | CONVERT | Edit Step 1. Reuse create_offer_s1 components with pre-populated data
edit_offer_s2.php | Page (Edit Step 2) | 171 | Very High | OfferModule: OfferService.updateStep2() | app/(offers)/[id]/edit/step2/page.tsx | OfferModule | CONVERT | Edit Step 2. 171KB. Break into reusable SKU row components
edit_offer_s3.php | Page (Edit Step 3) | 12 | Low | OfferModule: OfferService.updateStep3() | app/(offers)/[id]/edit/step3/page.tsx | OfferModule | CONVERT | Edit Step 3 confirmation
create_offer_s1_pitstop.php | Page (Pitstop S1) | 83 | High | OfferModule: CreatePitstopOfferDto | app/(offers)/pitstop/create/step1/page.tsx | OfferModule | MERGE+STRATEGY | Merge with create_offer_s1 using offer_type=PITSTOP strategy
create_offer_s2_pitstop.php | Page (Pitstop S2) | 122 | Very High | OfferModule: PitstopOfferStrategy.saveStep2() | app/(offers)/pitstop/create/step2/page.tsx | OfferModule | MERGE+STRATEGY | Use Strategy pattern with PITSTOP-specific fields
save_offer_pitstop.php | AJAX Handler | 48 | High | OfferModule: POST /offers (type=PITSTOP) | Next.js form submission → API | OfferModule | MERGE→API | Merge into single save endpoint with offer_type
create_offer_output_lc_view_pitstop.php | Report Page | 310 | Very High | FinanceModule: GET /financials/:id/output-lc (pitstop) | app/(offers)/pitstop/[id]/output/page.tsx | FinanceModule | MERGE+STRATEGY | Merge into OutputLCPage with pitstop variant logic
edit_offer_s1_pitstop.php | Page (Pitstop Edit) | 121 | Very High | OfferModule: PitstopOfferStrategy.update() | app/(offers)/pitstop/[id]/edit/step1/page.tsx | OfferModule | MERGE+STRATEGY | Reuse edit_offer_s1 with pitstop strategy
create_extended_offer_s1_iws.php | Page (IWS S1) | 65 | High | OfferModule: IWSOfferStrategy | app/(offers)/iws/create/step1/page.tsx | OfferModule | MERGE+STRATEGY | IWS = Industrial/Workshop. Strategy pattern
create_extended_offer_s2_iws.php | Page (IWS S2) | 95 | Very High | OfferModule: IWSOfferStrategy.saveStep2() | app/(offers)/iws/create/step2/page.tsx | OfferModule | MERGE+STRATEGY | IWS step 2
publish_offer.php | Page + Logic | 153 | Very High | OfferModule: POST /offers/:id/publish + PublishController | app/(offers)/[id]/publish/page.tsx | OfferModule | CONVERT→API+PAGE | 153KB. Extract Keris form, document upload, PO details into sub-components
approve_offer.php | Page + Logic | 148 | Very High | ApprovalModule: POST /approvals/:id/approve | app/(approvals)/[id]/approve/page.tsx | ApprovalModule | CONVERT→API+PAGE | 148KB. Approval chain logic → NestJS state machine service
approve_offer_pitstop.php | Page + Logic | 54 | High | ApprovalModule: PitstopApprovalStrategy | app/(approvals)/pitstop/[id]/approve/page.tsx | ApprovalModule | MERGE+STRATEGY | Pitstop approval → same approval controller with type flag
cancel_offer.php | Page + Logic | 29 | Medium | OfferModule: POST /offers/:id/cancel | app/(offers)/[id]/cancel/page.tsx | OfferModule | CONVERT→API | Cancel with reason + confirmation dialog
cancel_approval.php | Page + Logic | 45 | High | ApprovalModule: POST /approvals/:id/cancel | app/(approvals)/[id]/cancel/page.tsx | ApprovalModule | CONVERT→API | Cancel in-progress approval. Notify chain.
recall.php | Page + Logic | 23 | Medium | OfferModule: POST /offers/:id/recall | app/(offers)/[id]/recall/page.tsx | OfferModule | CONVERT→API | Recall published offer. Resets to draft. Notifies chain.
offer_pipeline_s1.php | Pipeline Page S1 | 16 | Medium | ApprovalModule: GET /approvals/pipeline (summary) | app/(pipeline)/page.tsx | ApprovalModule | CONVERT→PAGE | Pipeline dashboard list view
offer_pipeline_s2.php | Pipeline Page S2 | 111 | Very High | ApprovalModule: GET /approvals/pipeline (detail) | app/(pipeline)/details/page.tsx | ApprovalModule | CONVERT→PAGE | 111KB main pipeline view. Server component with react-table
offer_pipeline_s3.php | Pipeline Page S3 | 38 | High | ApprovalModule: GET /approvals/:id/history | app/(pipeline)/[id]/history/page.tsx | ApprovalModule | CONVERT→PAGE | Approval history timeline
offer_pipeline_s4_iws.php | Pipeline Page S4 IWS | 38 | High | ApprovalModule: IWS pipeline view | app/(pipeline)/iws/page.tsx | ApprovalModule | MERGE+STRATEGY | IWS-specific pipeline
nav_pipeline.php | Navigation | 13 | Medium | Frontend sidebar nav component | components/PipelineNav.tsx | Frontend Only | CONVERT→COMPONENT | Navigation menu → React sidebar component with active state
financials.php | Financial Calc Page | 63 | Very High | FinanceModule: FinancialCalcService | app/(offers)/[id]/financials/page.tsx | FinanceModule | CONVERT→SERVICE+PAGE | Core financial calculations. Extract all math to FinancialCalcService
financials_cs.php | CS Financials | 68 | Very High | FinanceModule: CSFinancialStrategy | Merged into financials page with type param | FinanceModule | MERGE+STRATEGY | CS (Customer Segment) variant. Merge with strategy.
financials_ts.php | TS Financials | 68 | Very High | FinanceModule: TSFinancialStrategy | Merged into financials page with type param | FinanceModule | MERGE+STRATEGY | TS variant. Merge.
financials_vs.php | VS Financials | 69 | Very High | FinanceModule: VSFinancialStrategy | Merged into financials page with type param | FinanceModule | MERGE+STRATEGY | VS variant. Merge.
output_lc.php | Output LC Report | 225 | Very High | FinanceModule: GET /financials/:id/output-lc | app/(reports)/output-lc/[id]/page.tsx | FinanceModule | CONVERT→SERVICE | 225KB letter of credit output. Split into sections.
data.php | Data View | 51 | Medium | FinanceModule: GET /offers/:id/data | app/(offers)/[id]/data/page.tsx | FinanceModule | CONVERT→PAGE | Financial data display with customer info
calculation.php | Excel Calc Include | 190 | Very High | FinanceModule: ExcelCalcService (included in report generation) | Backend service only | FinanceModule/ReportsModule | CONVERT→SERVICE | 190KB PHPExcel data. Port to ExcelJS calculation service.
formula_financial.php | Formula Include | 30 | High | FinanceModule: FinancialFormulaService (constants/formulas) | Backend service only | FinanceModule | CONVERT→SERVICE | Shared formula file. Extract all formulas to TypeScript constants + functions.
all_report.php | Report Page | 22 | Medium | ReportsModule: GET /reports/all-offers | app/(reports)/all-offers/page.tsx | ReportsModule | CONVERT→PAGE+API | All offers report with filters
anp_report.php | ANP Report | 8 | Low | ReportsModule: GET /reports/anp | app/(reports)/anp/page.tsx | ReportsModule | CONVERT→PAGE+API | ANP (Annual Net Profit?) report
input_tracker.php | Input Tracker | 11 | Medium | ReportsModule: GET /reports/input-tracker | app/(reports)/input-tracker/page.tsx | ReportsModule | CONVERT→PAGE+API | Input tracker report
commercial_input_view.php | Commercial Input | 69 | Very High | CommercialModule: CommercialController | app/(commercial)/[id]/page.tsx | CommercialModule | CONVERT→PAGE+API | 69KB Commercial input form. Break into tabs: Overview, SKU, Financials, Docs
ajax_sku_code.php | AJAX Endpoint | 15 | High | SKUModule: GET /sku/codes | API Only (called by React) | SKUModule | CONVERT→API | AJAX → REST API. Returns SKU list for offer creation.
ajax_download_excel_report.php | AJAX Download | 8 | Medium | ReportsModule: GET /downloads/offer-excel/:id | API Only (StreamableFile) | ReportsModule | CONVERT→API | Excel download. Use NestJS StreamableFile.
customer_get_ajax.php | AJAX Endpoint | 2 | Low | CustomerModule: GET /customers/search | API Only | CustomerModule | CONVERT→API | Customer search AJAX → REST GET endpoint
customer_set_ajax.php | AJAX Endpoint | 3 | Low | CustomerModule: POST /customers/set | API Only | CustomerModule | CONVERT→API | Customer association AJAX → REST POST
offer_pipeline_s3_ajax.php | AJAX Endpoint | 10 | Medium | ApprovalModule: GET /approvals/:id/pipeline-data | API Only | ApprovalModule | CONVERT→API | Pipeline AJAX → REST GET with offer ID
casn_report_pdf_none_type.php | PDF Generation | 106 | Very High | ReportsModule: GET /downloads/casn-pdf/:id | API Only (StreamableFile) | ReportsModule | CONVERT→PDF-SERVICE | 106KB CASN PDF. Use Puppeteer with React template.
casn_report_pdf_none_type_onfly.php | PDF On-Fly | 108 | Very High | ReportsModule: GET /downloads/casn-pdf/:id?mode=onfly | API Only | ReportsModule | MERGE | Merge into single endpoint with mode param.
pitstop_report_pdf_none_type.php | Pitstop PDF | 57 | High | ReportsModule: GET /downloads/pitstop-pdf/:id | API Only | ReportsModule | CONVERT→PDF-SERVICE | Pitstop CASN PDF.
sku_discount_generation_ftp_upload_daily.php | Daily Cron | 43 | High | CronModule: SkuDiscountCronService @Cron daily | Backend Cron Only | CronModule | CONVERT→CRON | Replace Linux crontab PHP call with NestJS @Cron scheduler
sku_discount_daily_live.php | Daily Discount Live | 45 | High | CronModule: SkuDiscountCronService (live channel) | Backend Cron Only | CronModule | MERGE | Merge live/daily variants into one configurable service
keris_submition_form.php | Page + Submit | 10 | Medium | IntegrationsModule: KerisService.submit() | app/(keris)/submit/page.tsx | IntegrationsModule | CONVERT→SERVICE+PAGE | Keris submission form. Wrap external API call.
keris_updation_form.php | Page + Update | 9 | Medium | IntegrationsModule: KerisService.update() | app/(keris)/update/page.tsx | IntegrationsModule | CONVERT→SERVICE+PAGE | Keris update form.
pid_mapping.php | PID Map Page | 82 | Very High | PIDModule: PIDController.getMapping() | app/(pid)/mapping/page.tsx | PIDModule | CONVERT→PAGE+API | 82KB PID mapping. Complex UI → react-table with server-side data
pidAdd.php | PID Add | 7 | Medium | PIDModule: POST /pid-mapping | Modal/form in PID page | PIDModule | CONVERT→API | PID add form → modal with API call
import_pid_details.php | PID Import | 14 | Medium | PIDModule: POST /pid-mapping/import (file upload) | app/(pid)/import/page.tsx | PIDModule | CONVERT→API | CSV/Excel PID import → Multer + service
reminder_mail_publish.php | Cron Mailer | 12 | Medium | CronModule: ReminderCronService + MailService | Backend Cron Only | CronModule+MailModule | CONVERT→CRON | Daily reminder for pending publish. @Cron + MailService.
reminder_mail_contract_extension.php | Cron Mailer | 11 | Medium | CronModule: ContractReminderCronService | Backend Cron Only | CronModule+MailModule | CONVERT→CRON | Contract extension reminder.
wbc_approval_pipeline_automailer.php | Approval Mailer | 15 | High | ApprovalModule: triggered by ApprovalService events | Backend Event Only | ApprovalModule+MailModule | CONVERT→EVENT | Event-driven: ApprovalService emits event → MailService handler
offer_closure_details.php | Closure Page | 19 | Medium | OfferClosureModule: GET /offer-closure/:id | app/(closure)/[id]/page.tsx | OfferClosureModule | CONVERT→PAGE+API | Offer closure data view
offer_closure_sku.php | Closure SKU | 15 | Medium | OfferClosureModule: POST /offer-closure/:id/sku | Closure form component | OfferClosureModule | CONVERT→API | SKU-level closure data entry
amendment_offer.php | Amendment Init | 5 | Low | OfferModule: GET /offers/:id/amendment-init | Redirect → Create Amendment flow | OfferModule | CONVERT→API | Initialize amendment from existing offer
change_sku_code.php | SKU Code Change | 20 | Medium | SKUModule: PATCH /sku/change | app/(admin)/sku-change/page.tsx | SKUModule | CONVERT→API+PAGE | SKU code change management
discount.php | Discount View | 10 | Medium | SKUModule: GET /sku/discount | app/(admin)/discounts/page.tsx | SKUModule | CONVERT→PAGE+API | Discount display
credit_input.php | Credit Input | 17 | Medium | CommercialModule: POST /commercial-input/:id/credit | app/(commercial)/[id]/credit/page.tsx | CommercialModule | CONVERT→API+PAGE | Credit rating input
approve_offer_31122025_abhinav.php | Backup File | 148 | — | DELETE — identical to approve_offer.php | N/A | — | DELETE | Bitwise identical backup. Safe to delete.
create_offer_s1_05012026.php | Backup File | 59 | — | DELETE — backup of create_offer_s1.php | N/A | — | DELETE | Dated backup. Delete after verifying active file is current.
output_lc_TEST.php | Test File | 224 | — | DELETE — test variant of output_lc.php | N/A | — | DELETE | Test file. Delete.

## 🗄️ DB Entity Map
DATABASE TABLE → TYPEORM ENTITY MAPPING
MySQL tables mapped to NestJS TypeORM entities with key columns and relations
PHP Table Name | TypeORM Entity Class | Module | Key Columns (Old → New) | PHP Serialized Fields (→ JSON) | Relations | Notes | Migration Effort | Action
wow_wo_offer_details | OfferEntity | OfferModule | offer_id→id(PK), offer_code, executive_code→userId, start_date, end_date, effective_end_date, offer_status→status(enum), is_pitstop, investment_type_text, offer_type_text, direct_customer_detail, indirect_customer_detail | sku_text (serialize→JSON), current_proposed_text (serialize→JSON), cogs_inflation_rate_percent (serialize→JSON), gross_turnover_inflation_rate_percent (serialize→JSON) | HasMany: OfferTransactionEntity HasOne: CustDetailsEntity HasMany: PODetailsEntity | Core offer table. 80% of queries hit this. Add indexes on offer_status, executive_code, effective_end_date. | 🔴 Very High | MIGRATE + REFACTOR
wow_wo_cust_details | CustDetailsEntity | CustomerModule | cid→id(PK), offer_id(FK), customer_name_text, customer_type_text, segment_text, customer_status_text, cust_state, country_name_text, commericial_input_compeleted_by_date | — | BelongsTo: OfferEntity BelongsTo: UserEntity | Customer data per offer. Normalize: extract customer master to separate table if not already. | 🟡 Medium | MIGRATE
wow_wo_offer_transaction | OfferTransactionEntity | ApprovalModule | id(PK), offer_id(FK), level, role_code, action_code, action_date, remarks, executive_code | — | BelongsTo: OfferEntity | Approval workflow history table. Each approval step = one row. Add proper indexes. | 🟡 Medium | MIGRATE
wow_wo_po_details | PODetailsEntity | OfferModule | po_id→id(PK), offer_id(FK), po_number, po_date, po_value, publish_offer_id | — | BelongsTo: OfferEntity | PO (Purchase Order) details linked to offers. | 🟢 Low | MIGRATE
wow_wo_fin_input | FinancialInputEntity | FinanceModule | id(PK), stock_days_int, creditor_days_int, cost_of_capital_int, cost_of_debt_int, wacc_int | — | Global singleton — no FK | Global financial parameters. Consider moving to .env or config service if rarely changes. | 🟢 Low | MIGRATE
wow_wo_sku_master / wow_wo_sku_code_change_master | SKUEntity / SKUChangeEntity | SKUModule | sku_id→id, sku_code, sku_name, list_price, cogs, category, old_sku_code, new_sku_code, status, effective_date | offer_details (serialize→JSON) in sku_code_change_master | HasMany: SKUChangeEntity | SKU master + code change history. JSON migration needed for offer_details column. | 🟡 Medium | MIGRATE + JSON-CONVERT
cilcc_cdr_test.econ_customers_drm | UserEntity | AuthModule | loginid→id(PK), name, email, password, roleid→role, status, zone, empcode | — | HasMany: OfferEntity (via executive_code) BelongsTo: RoleEntity | EXTERNAL DB TABLE (cilcc_cdr_test schema). Need to replicate in wow_db or join cross-schema. Critical for auth. | 🔴 Very High | REPLICATE/SYNC
cilcc_cdr_test.emp_mgr_map | ManagerMappingEntity | AuthModule | empcode→employeeCode, mgrcode→managerCode | — | BelongsTo: UserEntity (x2) | Employee-Manager hierarchy. Used for approval routing. Replicate or sync from CIL system. | 🔴 High | REPLICATE/SYNC
wow_wo_pid_mapping (inferred) | PIDMappingEntity | PIDModule | pid_id→id, offer_id(FK), parent_id, customer_code, status | — | BelongsTo: OfferEntity | PID (Parent ID) mapping for direct/distributor customers. | 🟡 Medium | MIGRATE
wow_wo_keris (inferred) | KerisSubmissionEntity | IntegrationsModule | keris_id→id, offer_id(FK), keris_code, submit_date, status, response | — | BelongsTo: OfferEntity | Keris integration submissions. Track submission status. | 🟡 Medium | MIGRATE
wow_wo_sku_discount (inferred) | SKUDiscountEntity | SKUModule | discount_id→id, sku_code, offer_id(FK), discount_value, effective_date, expiry_date, channel | — | BelongsTo: OfferEntity BelongsTo: SKUEntity | SKU discount records. Used in FTP upload daily job. | 🟡 Medium | MIGRATE
wow_wo_offer_closure (inferred) | OfferClosureEntity | OfferClosureModule | closure_id→id, offer_id(FK), sku_code, actual_volume, actual_gmpl, closure_date | — | BelongsTo: OfferEntity | Offer closure actuals vs planned. | 🟢 Low | MIGRATE
wow_wo_amendment_details (inferred) | AmendmentEntity | OfferModule | amendment_id→id, original_offer_id(FK), new_offer_id(FK), amendment_type, amendment_date | — | BelongsTo: OfferEntity (x2) | Amendment lineage tracking. parent_offer_id FK chain. | 🟡 Medium | MIGRATE
wow_wo_volume_plan (inferred) | VolumePlanEntity | OfferModule | plan_id→id, offer_id(FK), year, month, planned_volume, actual_volume | — | BelongsTo: OfferEntity | Monthly volume planning data. | 🟢 Low | MIGRATE

## 🗑️ Duplicate Files
DUPLICATE & BACKUP PHP FILES — SAFE TO DELETE
483 backup/variant files identified. Delete after migration to reduce confusion.
Backup File Name | Type | Size (bytes) | Active File | Identical? | Delete Safe?
approve_offer_31122025_abhinav.php | Developer Backup | 147846 | approve_offer.php | ✅ Yes | ✅ YES
approve_offer_11052026.php | Dated Backup | 147846 | approve_offer.php | ✅ Yes | ✅ YES
approve_offer_02012026.php | Dated Backup | 147894 | approve_offer.php | ❌ No (minor diff) | ⚠️ REVIEW
approve_offer_26112024.php | Dated Backup | 147878 | approve_offer.php | ❌ No | ⚠️ REVIEW
publish_offer_26052026.php | Dated Backup | 152993 | publish_offer.php | ✅ Yes | ✅ YES
publish_offer_23022026.php | Dated Backup | 152993 | publish_offer.php | ✅ Yes | ✅ YES
publish_offer_10042026.php | Dated Backup | 152993 | publish_offer.php | ✅ Yes | ✅ YES
publish_offer_report_02072023_abhishek.php | Dev Backup | 2052 | publish_offer_report.php | ✅ Yes | ✅ YES
Create_offer_s1_pitstop_18052026.php | Dated Backup | 83396 | create_offer_s1_pitstop.php | ✅ Yes | ✅ YES
create_offer_s1_pitstop_14012026_abhinav.php | Dev Backup | 83396 | create_offer_s1_pitstop.php | ✅ Yes | ✅ YES
create_offer_s1_pitstop_02042026.php | Dated Backup | 83396 | create_offer_s1_pitstop.php | ✅ Yes | ✅ YES
create_offer_s1_17022026.php | Dated Backup | 58582 | create_offer_s1.php | ✅ Yes | ✅ YES
edit_offer_s3_18052026.php | Dated Backup | 12414 | edit_offer_s3.php | ✅ Yes | ✅ YES
edit_offer_s1_pitstop_18062026.php | Dated Backup | 121130 | edit_offer_s1_pitstop.php | ✅ Yes | ✅ YES
edit_offer_s1_pitstop_21012025_abhinav.php | Dev Backup | 121130 | edit_offer_s1_pitstop.php | ✅ Yes | ✅ YES
edit_offer_s1_pitstop_14012026_abhinav.php | Dev Backup | 121130 | edit_offer_s1_pitstop.php | ✅ Yes | ✅ YES
edit_offer_s1_18052026.php | Dated Backup | 87524 | edit_offer_s1.php | ✅ Yes | ✅ YES
create_extended_offer_s1_iws_18062026.php | Dated Backup | 64797 | create_extended_offer_s1_iws.php | ✅ Yes | ✅ YES
Workbook_02062026.php | Dated Backup | 8505 | Workbook.php | ✅ Yes | ✅ YES
index_17042026.php | Dated Backup | 2057 | index.php | ✅ Yes | ✅ YES
pid_mapping_09022026.php | Dated Backup | 82240 | pid_mapping.php | ✅ Yes | ✅ YES
wbc_report_sku_cron_prod_target_download_29042026.php | Dated Backup | 22022 | wbc_report_sku_cron_prod_target_download.php | ✅ Yes | ✅ YES
ws_report_pdf_none_type_onfly_02012025.php | Dated Backup | 41166 | ws_report_pdf_none_type_onfly.php | ✅ Yes | ✅ YES
backup.zip | Archive | 145060831 | N/A | N/A | ⚠️ ARCHIVE EXTERNALLY
backup_22052026.zip | Archive | 73966080 | N/A | N/A | ⚠️ ARCHIVE EXTERNALLY
test.php | Test File | 2648 | N/A | N/A | ✅ DELETE
test2.php | Test File | 18 | N/A | N/A | ✅ DELETE
output_lc_TEST.php | Test File | 224071 | output_lc.php | ❌ No | ✅ DELETE
output_lc_WORKING.php | Working Copy | 224036 | output_lc.php | ✅ Yes | ✅ DELETE
testingname.php | Test File | 39 | N/A | N/A | ✅ DELETE
file_test.php | Test File | 22 | N/A | N/A | ✅ DELETE
phpinfo.php | Debug File | 19 | N/A | N/A | 🔴 DELETE (security risk)
attechment_test_chintak.php | Test File | 409 | N/A | N/A | ✅ DELETE
mailer_test.php | Test File | 0 | N/A | N/A | ✅ DELETE
pid_count_testing.php | Test File | 1798 | N/A | N/A | ✅ DELETE
sku_add_test.php | Test File | 3597 | N/A | N/A | ✅ DELETE
sku_addition_test.php | Test File | 3483 | N/A | N/A | ✅ DELETE
multi_sku_code.php | Empty File | 0 | N/A | N/A | ✅ DELETE
refractor.php | Empty File | 0 | N/A | N/A | ✅ DELETE
testingnavpipeline.php | Empty File | 0 | N/A | N/A | ✅ DELETE
cancel_offer_test.php | Test File | 12554 | cancel_offer.php | ❌ No | ⚠️ REVIEW
publish_offer_test.php | Test File | 84998 | publish_offer.php | ❌ No | ⚠️ REVIEW
edit_offer_output_lc_view_simulation.php | Simulation | 243775 | edit_offer_output_lc_view.php | ❌ No | ⚠️ KEEP UNTIL SIMULATION PORTED
edit_offer_simulation_pdf.php | Simulation | 80383 | N/A | N/A | ⚠️ KEEP UNTIL SIMULATION PORTED
create_offer_16012026_abhinav.php | Dev Branch | 157899 | create_offer_s2.php? | ❌ No | ⚠️ REVIEW
approve_offerORG.php | Original Copy | 9199 | N/A | N/A | ⚠️ REVIEW (historical reference)
offer_pipeline_s2ORG.php | Original Copy | 20870 | offer_pipeline_s2.php | ❌ No | ⚠️ REVIEW
Ammedent.zip | Old Archive | 90989 | N/A | N/A | ⚠️ ARCHIVE EXTERNALLY
Archive.zip | Old Archive | 473654 | N/A | N/A | ⚠️ ARCHIVE EXTERNALLY

## 🏗️ NestJS Structure
NESTJS + NEXTJS PROJECT STRUCTURE
Recommended monorepo folder structure for the new architecture
File / Folder Path | Type | Purpose
📁 wow-genie/ (monorepo root) | Root | Monorepo root with Turborepo or Nx
├── 📁 apps/ | Directory | Applications
│ ├── 📁 api/ (NestJS) | NestJS App | Backend API server
│ │ ├── src/ | Source Root | NestJS source root
│ │ ├── src/app.module.ts | Root Module | AppModule — registers all feature modules
│ │ ├── src/main.ts | Entry Point | NestJS bootstrap, Swagger setup, global pipes/guards
│ │ ├── src/modules/ | Modules Dir | All feature modules
│ │ ├── src/modules/auth/ | AuthModule | auth.module.ts, auth.controller.ts, auth.service.ts, jwt.strategy.ts, roles.guard.ts
│ │ ├── src/modules/offer/ | OfferModule | offer.module.ts, offer.controller.ts, offer.service.ts, offer.entity.ts, dtos/
│ │ ├── src/modules/approval/ | ApprovalModule | approval.module.ts, approval.controller.ts, approval.service.ts, dofa.service.ts
│ │ ├── src/modules/finance/ | FinanceModule | financial-calc.service.ts, irr-npv.service.ts, output-lc.service.ts
│ │ ├── src/modules/sku/ | SKUModule | sku.module.ts, sku.service.ts, sku-discount.service.ts
│ │ ├── src/modules/customer/ | CustomerModule | customer.module.ts, customer.service.ts
│ │ ├── src/modules/pid/ | PIDModule | pid.module.ts, pid.service.ts
│ │ ├── src/modules/reports/ | ReportsModule | reports.module.ts, excel.service.ts, pdf.service.ts
│ │ ├── src/modules/commercial/ | CommercialModule | commercial.module.ts, commercial.service.ts
│ │ ├── src/modules/offer-closure/ | OfferClosureModule | offer-closure.module.ts, offer-closure.service.ts
│ │ ├── src/modules/mail/ | MailModule | mail.module.ts, mail.service.ts, templates/ (HBS)
│ │ ├── src/modules/cron/ | CronModule | cron.module.ts, sku-discount.cron.ts, reminder.cron.ts, contract.cron.ts
│ │ ├── src/modules/integrations/ | IntegrationsModule | sftp.service.ts, keris.service.ts, ftp-upload.service.ts
│ │ ├── src/modules/admin/ | AdminModule | admin.module.ts, admin.controller.ts, financial-input.service.ts
│ │ ├── src/modules/uploads/ | UploadsModule | uploads.module.ts, uploads.service.ts, multer.config.ts
│ │ ├── src/common/ | Common | decorators/, pipes/, interceptors/, filters/, guards/
│ │ ├── src/common/decorators/roles.decorator.ts | Decorator | @Roles() decorator — maps to RolesGuard
│ │ ├── src/common/guards/jwt-auth.guard.ts | Guard | JwtAuthGuard — validates JWT on all protected routes
│ │ ├── src/common/guards/roles.guard.ts | Guard | RolesGuard — checks user role against @Roles()
│ │ ├── src/common/interceptors/response.interceptor.ts | Interceptor | Wraps all responses in {success, data, message, timestamp}
│ │ ├── src/common/filters/http-exception.filter.ts | Filter | Global error handler — consistent error response format
│ │ ├── src/common/utils/formatters.ts | Utility | moneyFormatIndia(), formatDate(), round() helpers
│ │ ├── src/common/utils/crypto.util.ts | Utility | encrypt/decrypt offer IDs (port from core_decrypt.php)
│ │ ├── src/config/ | Config | database.config.ts, mail.config.ts, sftp.config.ts, jwt.config.ts
│ │ ├── src/database/ | Database | migrations/, seeds/, typeorm.config.ts
│ │ ├── src/database/migrations/ | Migrations | TypeORM migration files for schema + data conversion
│ │ ├── src/enums/offer-status.enum.ts | Enum | OfferStatus: D/P/A/E/C/I + offer_type: STANDARD/PITSTOP/IWS/TATAPCD
│ │ ├── src/enums/role.enum.ts | Enum | Role: WS, ASM, KAS, SAM, RWM, WSM, CM, VPB2B, DA, DF, RF, RVP, GMWBC
│ │ └── test/ | Tests | unit/ + e2e/ test directories
│ └── 📁 web/ (Next.js 14) | Next.js App | Frontend App Router application
│ ├── app/ | App Router | Next.js 14 App Router root
│ ├── app/(auth)/login/page.tsx | Login Page | Login form → calls POST /auth/login
│ ├── app/(auth)/forgot-password/page.tsx | Forgot Pwd | Forgot password → POST /auth/send-password
│ ├── app/(dashboard)/page.tsx | Dashboard | Role-based dashboard with quick stats
│ ├── app/(offers)/create/ | Create Offer | Multi-step wizard: step1/, step2/, step3/ pages
│ ├── app/(offers)/[id]/edit/ | Edit Offer | Edit steps: step1/, step2/, step3/
│ ├── app/(offers)/[id]/financials/page.tsx | Financials | Financial calculations view (replaces financials.php)
│ ├── app/(offers)/[id]/output/page.tsx | Output LC | Output LC view (replaces output_lc.php)
│ ├── app/(offers)/pitstop/ | Pitstop Offers | Pitstop offer create/edit/view (strategy pattern)
│ ├── app/(offers)/iws/ | IWS Offers | IWS offer create/edit/view
│ ├── app/(pipeline)/page.tsx | Pipeline | Approval pipeline list (replaces offer_pipeline_s1/s2)
│ ├── app/(pipeline)/[id]/page.tsx | Pipeline Detail | Offer detail in pipeline (replaces offer_pipeline_s3)
│ ├── app/(approvals)/[id]/approve/page.tsx | Approve Offer | Approval action page (replaces approve_offer.php)
│ ├── app/(reports)/ | Reports | All report pages
│ ├── app/(admin)/ | Admin | Admin pages: financial input, DOFA config, SKU management
│ ├── components/ | Components | Shared React components
│ ├── components/offer/ | Offer Components | OfferCard, OfferStatus, SKUTable, FinancialSummary, etc.
│ ├── components/approval/ | Approval Components | ApprovalChain, ApprovalHistory, DOFADisplay
│ ├── components/forms/ | Form Components | Multi-step form wizard, SKU row, PID row, date pickers
│ ├── components/ui/ | UI Library | Button, Modal, Table, Badge, Toast, Sidebar, DataTable
│ ├── hooks/ | Custom Hooks | useRolePermissions(), useOfferForm(), usePagination()
│ ├── lib/api/ | API Client | axios instance + typed API functions per module
│ ├── lib/api/offer.api.ts | Offer API | createOffer(), updateOffer(), getOffer(), etc.
│ ├── lib/api/auth.api.ts | Auth API | login(), logout(), me(), refreshToken()
│ ├── lib/store/ | State Store | Redux Toolkit slices: authSlice, offerSlice
│ ├── lib/validations/ | Zod Schemas | offerSchema.ts, approvalSchema.ts, etc.
│ └── lib/utils/ | Utils | formatters.ts, dateUtils.ts, constants.ts
└── 📁 packages/ | Shared Packages | Shared types/DTOs between FE and BE
├── 📁 shared-types/ | Shared Types | TypeScript interfaces shared by both apps
│ ├── offer.types.ts | Offer Types | IOfferDto, ICreateOfferDto, IOfferResponse — shared
│ ├── user.types.ts | User Types | IUserDto, Role enum — shared
│ └── financial.types.ts | Financial Types | IFinancialCalc, IIRR, INPV — shared
└── 📁 config/ | Shared Config | eslint, tsconfig, prettier config shared across apps

## ⚠️ Risk Register
MIGRATION RISK REGISTER
Identified risks, impacts, and mitigation strategies for the PHP → NestJS migration
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Mitigation Strategy
R-01 | PHP serialize() data in DB — wow_wo_offer_details columns (sku_text, current_proposed_text) use PHP serialize(). Node.js cannot read this natively. | Data Migration | 🔴 High | 🔴 Critical | 9/9 | 1. Write one-time PHP migration script to convert all serialized columns to JSON. 2. Add JSON type column alongside old column. 3. Dual-write during transition. 4. Cutover when all rows migrated. 5. Add unit tests comparing old vs new data.
R-02 | Cross-schema DB queries — code queries cilcc_cdr_test.econ_customers_drm (separate DB/schema) for user auth data. | Database | 🔴 High | 🔴 High | 8/9 | 1. Identify all cross-DB queries. 2. Replicate user table into wow_db or create microservice. 3. Implement data sync job from CIL system. 4. Use TypeORM cross-schema support if on same MySQL instance.
R-03 | Financial calculation accuracy — IRR/NPV/GM calculations in PHP must produce identical results in NestJS. Any difference breaks business sign-offs. | Business Logic | 🔴 High | 🔴 Critical | 9/9 | 1. Create regression test suite with 50+ real offer datasets. 2. Port PHP financial formulas to TypeScript, use financial.js or custom IRR bisection. 3. Run PHP vs Node.js outputs side by side for each offer. 4. Get finance team sign-off before cutover.
R-04 | Massive file size — create_offer_output_lc_view.php is 326KB, output_lc.php is 225KB. These mix HTML, PHP logic, and SQL queries throughout. Very hard to decompose. | Complexity | 🔴 High | 🟡 Medium | 6/9 | 1. Use Strangler Fig: serve new NestJS page for new offers, PHP for old offers initially. 2. Extract SQL queries first, then business logic, then HTML rendering. 3. Break into small React components. 4. Use React Server Components for data fetching.
R-05 | Session-based auth → JWT migration — all 50+ PHP files use $_SESSION. Existing users have active sessions that will break at cutover. | Authentication | 🟡 Medium | 🔴 High | 6/9 | 1. Implement JWT auth in parallel. 2. Use nginx reverse proxy to route /api/* to NestJS and / to PHP. 3. Plan a maintenance window for session cutover. 4. Implement refresh token rotation.
R-06 | Role-based access — PHP uses hardcoded $login_array arrays, sometimes with employee codes (83100555) instead of role names. Mapping is inconsistent across files. | Authorization | 🔴 High | 🟡 Medium | 6/9 | 1. Audit all role arrays across all 50+ files. 2. Create comprehensive Role enum mapping. 3. Test all role-specific workflows with each role type. 4. Implement feature flags for role-specific features during transition.
R-07 | Offer type variants (Standard, Pitstop, IWS, TataPCD) — 30+ file pairs exist for each variant. Missing business rules documentation for what differs between variants. | Business Rules | 🔴 High | 🔴 High | 8/9 | 1. Document exact differences between Standard vs Pitstop vs IWS vs TataPCD workflows. 2. Get business stakeholder sign-off on differences. 3. Implement Strategy pattern — shared base + variant-specific overrides. 4. Comprehensive test matrix per offer type.
R-08 | Data volume — WBCOFFER_DG_20241217.csv is 4.8MB. DB may have millions of rows in offer tables. Migration scripts must handle large data gracefully. | Data Migration | 🟡 Medium | 🟡 Medium | 4/9 | 1. Test migration scripts on prod-sized data snapshot. 2. Use batch processing (1000 rows/batch). 3. Run migration in off-hours. 4. Implement rollback scripts.
R-09 | SFTP / FTP integrations — phpseclib SSH2 for SFTP. Credentials hardcoded or in PHP config. SFTP endpoints may differ in Node.js environment. | Integration | 🟡 Medium | 🟡 Medium | 4/9 | 1. Extract all SFTP credentials to .env. 2. Test ssh2-sftp-client against same SFTP server. 3. Implement retry logic + alerts on SFTP failure. 4. Monitor SFTP jobs with NestJS health checks.
R-10 | Email deliverability — PHPMailer is deeply embedded. Email templates are hardcoded HTML strings in PHP. Thousands of emails may be in-flight during migration. | Integration | 🟡 Medium | 🟡 Medium | 4/9 | 1. Test Nodemailer with same SMTP server. 2. Build Handlebars templates matching existing email HTML. 3. Run dual-send test period. 4. Implement email queue with Bull to prevent loss.
R-11 | PHPExcel → ExcelJS differences — cell styling, number formats, merged cells may look different. Business users compare outputs visually. | Reports | 🟡 Medium | 🟡 Medium | 4/9 | 1. Get sample Excel outputs signed off by stakeholders. 2. Match column widths, colors, number formats exactly. 3. Run visual comparison tests on 20+ sample reports. 4. Use ExcelJS style APIs carefully.
R-12 | PDF rendering differences — TCPDF vs Puppeteer HTML→PDF. Fonts, page breaks, and table borders may differ. CASN PDF is used in legal/contract contexts. | Reports | 🔴 High | 🔴 High | 8/9 | 1. Pixel-compare PDF outputs using pdf-diff tool. 2. Get legal/business approval on new PDF format. 3. Consider wkhtmltopdf if Puppeteer output differs too much. 4. Phase: serve PHP PDF initially, migrate after approval.
R-13 | Knowledge gap — PHP codebase has no documentation. Business logic is embedded in 483 files with developer names/dates in filenames. Key developers may not be available. | Knowledge | 🟡 Medium | 🔴 High | 6/9 | 1. Run code archaeology sessions — map each active file to business function. 2. Interview key users to validate migration. 3. Keep PHP code running in parallel for 6 months minimum. 4. Document all business rules discovered during migration.
R-14 | Zero automated tests in PHP — no unit, integration, or e2e tests. High risk of silent regressions during migration. | Quality | 🔴 High | 🔴 High | 8/9 | 1. Write regression test suite BEFORE migration, using real data. 2. Set test coverage target: 80% for NestJS services. 3. Add E2E tests with Playwright for critical paths. 4. CI/CD gate: block deploy if tests fail.
R-15 | Cron job timing — PHP cron jobs triggered by Linux crontab. NestJS scheduler runs in-process. If API restarts, running crons may be interrupted. | Infrastructure | 🟡 Medium | 🟡 Medium | 4/9 | 1. Use NestJS @nestjs/schedule for simple crons. 2. For critical jobs (SKU discount daily), use Bull queue with Redis for reliability. 3. Add health check endpoint to monitor cron status. 4. Implement idempotent cron logic (safe to re-run).

## 📅 Sprint Plan
SPRINT-BY-SPRINT MIGRATION PLAN
21-Sprint (21 week) detailed delivery plan — Strangler Fig approach
Sprint | Weeks | Phase | Goal | NestJS Tasks | Next.js Tasks | Acceptance Criteria | Owner
S-01 | W1-W2 | Foundation | Setup monorepo, CI/CD, DB connectivity | 1. nx/turborepo workspace init 2. NestJS app scaffold 3. TypeORM + MySQL connection 4. JWT auth foundation 5. ENV config module 6. Swagger setup 7. Global interceptor + filter | 1. Next.js 14 App Router setup 2. Login page UI 3. Axios API client config 4. Redux Toolkit + auth slice 5. Tailwind/CSS design system | ✅ API server starts ✅ DB connection works ✅ Login returns JWT ✅ Next.js builds cleanly | Tech Lead
S-02 | W3-W4 | Auth & Users | Complete auth module + user management | 1. UserEntity (from cilcc_cdr.econ_customers_drm) 2. AuthService: login, logout, refresh 3. JWT Strategy + RolesGuard 4. Role enum (WS,ASM,KAS,SAM,RWM,CM,VPB2B...) 5. POST /auth/send-password 6. Cross-schema user query setup | 1. Login page form + validation 2. Auth context / Redux integration 3. Protected route wrapper 4. Role-based nav sidebar 5. Forgot password page | ✅ All roles can login ✅ JWT validates correctly ✅ Role guard blocks unauthorized access ✅ Logout clears token | BE Dev + FE Dev
S-03 | W5-W6 | Offer Core | Create Offer Step 1 + basic CRUD | 1. OfferEntity + migrations 2. CreateOfferDto (step1 fields) 3. POST /offers (create) 4. GET /offers/:id 5. OfferValidationService (date, SKU, PID) 6. WBC number generation | 1. Create Offer Step 1 page (React Hook Form + Zod) 2. Customer search (GET /customers/search) 3. Date pickers, offer type selection 4. Offer type strategy selection (Standard/Pitstop/IWS) | ✅ Can create a new standard offer ✅ WBC number generated correctly ✅ Step 1 validation works ✅ Customer search returns results | Full Stack
S-04 | W7-W8 | Offer Core | Create Offer Step 2 (SKU + Pricing) | 1. SKUEntity + DiscountEntity 2. GET /sku/codes endpoint 3. SKUValidationService 4. OfferService.saveStep2() 5. Duplicate PID validation 6. Volume + pricing fields | 1. Create Offer Step 2 page — SKU table (react-table) 2. Dynamic SKU row add/remove 3. Pricing input fields per SKU 4. Real-time discount calculation 5. Save draft functionality | ✅ Can add 5+ SKUs to offer ✅ Pricing calculates correctly ✅ Duplicate PID check works ✅ Draft saves to DB | Full Stack
S-05 | W9 | Offer Core | Create Offer Step 3 + Save | 1. OfferService.saveStep3() confirmation 2. POST /offers/:id/save (final) 3. Offer status: D→ready_to_publish 4. Document upload endpoint | 1. Step 3 confirmation page 2. Summary of all entered data 3. Submit for publish action 4. File upload component | ✅ Complete offer creation flow works end-to-end ✅ Offer saved in DB with all sections ✅ Can view created offer | Full Stack
S-06 | W10 | Publish Flow | Publish offer + basic approval | 1. POST /offers/:id/publish 2. ApprovalEntity + transaction 3. First approver notification email 4. MailService (Nodemailer + HBS) 5. ApprovalService.getNextApprover() | 1. Publish Offer page (Keris form, PO details, docs) 2. Submit for approval action 3. Offer status badge component 4. Email preview in UI | ✅ Can publish offer ✅ Approval email sent to WS/RWM ✅ Offer shows 'Pending' status ✅ Email HTML matches PHP email format | Full Stack + QA
S-07 | W11-W12 | Approval Chain | Full approval workflow + DOFA | 1. POST /approvals/:id/approve per level 2. DOFA logic: WS→RWM→GMWBC→CM→VPB2B→DA→DF→RF→RVP 3. Role-based approval routing 4. POST /approvals/:id/reject 5. Notification per level change 6. GET /approvals/pipeline | 1. Approval pipeline list (server component + table) 2. Approve/Reject action modals 3. Approval chain progress indicator 4. Pipeline filters (role, status, date) 5. Mobile-responsive pipeline view | ✅ All 9 approval levels work correctly ✅ Only correct role can approve at each level ✅ Rejected offers return to WS ✅ Pipeline shows correct offers per role | Full Stack + BA
S-08 | W13 | Offer Lifecycle | Cancel, Recall, Extend, Amend | 1. POST /offers/:id/cancel (with reason) 2. POST /offers/:id/recall 3. POST /offers/:id/extend (new end date) 4. POST /offers/:id/amend (parent_offer_id chain) 5. Status transition validations | 1. Cancel offer modal + reason input 2. Recall offer confirmation 3. Extend offer date picker 4. Amend flow (redirects to create with pre-fill) 5. Status transition history timeline | ✅ All lifecycle transitions work ✅ Emails sent on each transition ✅ Offer history shows all actions ✅ Amendment links to parent offer | Full Stack
S-09 | W14-W15 | Financials | Financial calculations + Output LC | 1. FinancialCalcService (port financials.php) 2. IRR/NPV calculation (port PHP bisection) 3. GM Pool / GM P/L calculation 4. GET /financials/:id 5. GET /financials/:id/output-lc 6. Inflation rate computation | 1. Financials view page (replaces financials.php) 2. Output LC page (replaces output_lc.php) 3. Financial summary tables 4. Year-wise breakdowns 5. IRR/NPV display with chart | ✅ IRR/NPV match PHP calculations for 20+ test offers ✅ GM Pool matches PHP output ✅ Finance team sign-off on calculations ✅ Output LC page matches PHP visually | BE Dev (Finance) + QA
S-10 | W16 | Reports Basic | Excel + PDF report generation | 1. ExcelService using ExcelJS 2. Port calculation.php → ExcelCalcService 3. GET /downloads/offer-excel/:id 4. PDFService using Puppeteer 5. GET /downloads/casn-pdf/:id | 1. Download Excel button on offer pages 2. Download PDF button 3. Report filters UI 4. Loading state during generation | ✅ Excel downloads match PHP Excel format ✅ CASN PDF matches PHP PDF visually ✅ Stakeholder sign-off on report formats | BE Dev + QA
S-11 | W17 | Pitstop Offers | Pitstop offer create/edit/approve flow | 1. PitstopOfferStrategy (implements OfferStrategy) 2. Pitstop-specific fields + validation 3. Pitstop output LC endpoint 4. Pitstop approval chain (may differ) | 1. Pitstop create offer wizard 2. Pitstop-specific form fields 3. Pitstop pipeline view 4. Pitstop output LC page | ✅ Pitstop offer creation works ✅ Pitstop-specific fields visible/hidden correctly ✅ Pitstop approval chain correct | Full Stack
S-12 | W18 | IWS Offers | IWS extended offer flow | 1. IWSOfferStrategy 2. IWS-specific endpoints 3. IWS pipeline (offer_pipeline_s4_iws port) 4. IWS reports | 1. IWS create offer wizard 2. IWS pipeline page 3. IWS report pages | ✅ IWS offer creation works ✅ IWS pipeline shows correct offers ✅ IWS reports generate correctly | Full Stack
S-13 | W19 | Cron & Integrations | Cron jobs + SFTP + Keris | 1. @nestjs/schedule CronModule 2. SkuDiscountCronService (@Cron daily) 3. ReminderCronService (contract, publish) 4. SFTPService (ssh2-sftp-client) 5. KerisService (submit, update, status) 6. Bull queue for critical jobs | 1. Keris submission form 2. Keris update form 3. Admin: manual cron trigger UI 4. Cron job status dashboard | ✅ SKU discount cron generates correct file ✅ SFTP upload succeeds ✅ Reminder emails sent on schedule ✅ Keris submission works | BE Dev + DevOps
S-14 | W20 | Admin & Config | Admin module + settings | 1. AdminModule: DOFA config CRUD 2. Financial input CRUD 3. User management (if needed) 4. System health endpoint 5. Bulk SKU operations | 1. Admin dashboard 2. DOFA configuration UI 3. Financial input form 4. SKU management pages 5. User management (if applicable) | ✅ Admin can update DOFA config ✅ Financial input saves correctly ✅ Changes reflect in offer calculations | Full Stack + Admin
S-15 | W21 | QA & Cutover | Final testing + data migration + go-live | 1. Data migration scripts (serialize→JSON) 2. Cross-DB user data migration 3. Performance testing (load test) 4. Security audit (OWASP) 5. Final regression suite | 1. E2E tests with Playwright 2. Browser compatibility testing 3. Mobile responsive validation 4. Accessibility audit (WCAG) 5. User acceptance testing with stakeholders | ✅ All critical paths pass E2E ✅ Performance: <2s page load ✅ Zero data loss in migration ✅ Business sign-off obtained ✅ Rollback plan tested | Full Team + QA + BA

## 💡 Code Conversion Guide
PHP → TYPESCRIPT/NESTJS CODE CONVERSION GUIDE
Side-by-side PHP patterns and their NestJS/TypeScript equivalents
Pattern / Context | PHP Code (Old) | NestJS/TypeScript Code (New) | Notes | Where Used
Session Auth Check | session_start(); $sessionRole = $_SESSION['user_rolecode_s']; $sessionCode = $_SESSION['usercode_s']; if($sessionCode == "") { echo "session_logout"; exit(); } | // auth.controller.ts @UseGuards(JwtAuthGuard) @Get('me') async getProfile(@CurrentUser() user: UserPayload) { return user; } // jwt-auth.guard.ts extends AuthGuard('jwt') // Applied globally via APP_GUARD or per-controller | Every PHP file starts with this. Replace with global JwtAuthGuard. Custom @CurrentUser() decorator extracts user from JWT payload. | save_offer, approve_offer, publish_offer, ALL
Role Check | if($sessionRole == "WS" ¦¦ $sessionRole == "ASM" ¦¦ $sessionRole == "KAS") { // allow access } | // roles.decorator.ts export const Roles = (...roles: Role[]) => SetMetadata('roles', roles); // offer.controller.ts @Post() @Roles(Role.WS, Role.ASM, Role.KAS) @UseGuards(JwtAuthGuard, RolesGuard) async createOffer(@Body() dto: CreateOfferDto) { return this.offerService.create(dto); } | Inline role checks → declarative @Roles() decorator + RolesGuard reads metadata to allow/deny. | create_offer_s1, publish_offer, 20+ files
Raw SQL Query | $query = "SELECT a.*, b.*, c.* FROM wow_wo_offer_details a LEFT JOIN wow_wo_po_details b ON a.offer_id=b.offer_id INNER JOIN wow_wo_cust_details c ON a.offer_id=c.offer_id WHERE a.offer_status='P' AND po_date BETWEEN '$from' AND '$to'"; $res = mysqli_query($conn, $query) or die(mysqli_error($conn)); while($row = mysqli_fetch_assoc($res)) { // process row } | // offer.repository.ts (TypeORM QueryBuilder) async findPendingByDateRange(from: Date, to: Date) { return this.offerRepo .createQueryBuilder('offer') .leftJoinAndSelect('offer.poDetails', 'po') .innerJoinAndSelect('offer.custDetails', 'cust') .where("offer.status = :status", { status: 'P' }) .andWhere("po.poDate BETWEEN :from AND :to", { from, to }) .getMany(); } | mysqli raw SQL → TypeORM QueryBuilder. Parameterized queries prevent SQL injection. Strong typing via entity relations. | calculation.php, offer_list.php, all_report.php
PHP serialize → JSON | // Writing: $sku_text = serialize($sku_array); $query = "UPDATE wow_wo_offer_details SET sku_text='$sku_text' WHERE offer_id=$id"; // Reading: $sku_table = unserialize($row['sku_text']); $volume = $sku_table['tot_volume']; | // offer.entity.ts @Entity() export class OfferEntity { @Column({ type: 'json', nullable: true }) skuData: SkuDataDto[]; // JSON column } // Writing: offer.skuData = skuArray; // auto-serialized to JSON await this.offerRepo.save(offer); // Reading: const volume = offer.skuData.reduce( (sum, sku) => sum + sku.volume, 0); | PHP serialize() → MySQL JSON column. One-time migration script needed to convert existing serialized data. TypeORM @Column({type:'json'}) auto-handles JSON parse/stringify. | wow_wo_offer_details.sku_text, current_proposed_text
Email Sending | require("class.phpmailer.php"); $mail = new PHPMailer(); $mail->IsSMTP(); $mail->Host = "mail.example.com"; $mail->From = "admin@wow.com"; $mail->AddAddress($to); $mail->Subject = "Approval Required"; $mail->IsHTML(true); $mail->Body = "<b>Hello " .$name. "</b>..."; $mail->Send(); | // mail.service.ts @Injectable() export class MailService { constructor( private mailerService: MailerService ) {} async sendApprovalEmail(offer: Offer, to: string) { await this.mailerService.sendMail({ to, subject: 'Approval Required', template: 'approval', // templates/approval.hbs context: { offerCode: offer.offerCode, customerName: offer.custDetails.name, }, }); } } | PHPMailer → @nestjs-modules/mailer with Nodemailer. HTML string → Handlebars .hbs template file. Queue with Bull for reliability. | recall.php, publish_offer.php, wbc_approval_pipeline_automailer.php
IRR/NPV Calculation | // financials.php — IRR calculation function irr_calculate($investment, $cashflows) { $guess = 0.1; for($i=0; $i<100; $i++) { $npv = $investment; foreach($cashflows as $y=>$cf) { $npv += $cf / pow(1+$guess, $y+1); } if(abs($npv) < 0.001) break; $guess = $guess + ($npv > 0 ? 0.001 : -0.001); } return $guess * 100; } | // financial-calc.service.ts calculateIRR(initialInvestment: number, cashflows: number[]): number { let guess = 0.1; for (let i = 0; i < 1000; i++) { let npv = initialInvestment; cashflows.forEach((cf, year) => { npv += cf / Math.pow(1 + guess, year + 1); }); if (Math.abs(npv) < 0.0001) break; guess += npv > 0 ? 0.001 : -0.001; } return parseFloat((guess * 100).toFixed(4)); } calculateNPV(rate: number, cashflows: number[]): number { return cashflows.reduce((npv, cf, i) => npv + cf / Math.pow(1 + rate / 100, i + 1), 0); } | Port bisection method for IRR from PHP. Validate against 20+ real offers. Consider using financial.js npm package for battle-tested implementation. | financials.php, output_lc.php, financials_cs/ts/vs.php
Indian Money Format | function moneyformatindia($n) { $n = (float)$n; if($n >= 10000000) { $n = round($n/10000000, 2) . ' Cr.'; } elseif($n >= 100000) { $n = round($n/100000, 2) . ' Lac'; } elseif($n >= 1000) { $n = round($n/1000, 2) . ' K'; } return $n; } | // utils/formatters.ts export function moneyFormatIndia( value: number, decimals = 2 ): string { const n = Number(value); if (n >= 10_000_000) return `${(n / 10_000_000).toFixed(decimals)} Cr.`; if (n >= 100_000) return `${(n / 100_000).toFixed(decimals)} Lac`; if (n >= 1_000) return `${(n / 1_000).toFixed(decimals)} K`; return n.toFixed(decimals); } // Use in both NestJS and Next.js (shared package) | Pure utility function. Shared in packages/shared-utils. Used in both NestJS API responses and Next.js display components. | recall.php, output_lc.php, financials.php, 15+ files
Decrypt Offer ID | // core_decrypt.php function core_decrypt($val) { return base64_decode($val); // or custom decrypt logic } // Usage: $id = core_decrypt($_GET['offerID']); $query = "SELECT * FROM offers WHERE offer_id=$id"; | // crypto.util.ts import { createCipheriv, createDecipheriv } from 'crypto'; export function decryptOfferId(encrypted: string): number { // If simple base64: return parseInt(atob(encrypted)); // If AES: use crypto.createDecipheriv() const decoded = Buffer.from(encrypted, 'base64').toString(); return parseInt(decoded); } // offer.controller.ts @Get(':id') async getOffer(@Param('id') encryptedId: string) { const id = decryptOfferId(encryptedId); return this.offerService.findOne(id); } | Port core_decrypt() to TypeScript. Consider migrating to standard UUIDs for new offers instead. Keep backward compat for old encrypted IDs. | financials.php, data.php, recall.php, 30+ files
Cron Job (Daily FTP Upload) | // Linux crontab entry: // 0 0 * * * php /path/to/sku_discount_generation_ftp_upload_daily.php // Inside PHP file: // No structure — procedural script // Connects to DB, generates CSV, uploads via phpseclib SFTP $sftp = new Net_SFTP($host); $sftp->login($user, $pass); $sftp->put($remotePath, $csvContent); | // sku-discount.cron.ts @Injectable() export class SkuDiscountCron { constructor( private skuDiscountSvc: SkuDiscountService, private sftpSvc: SFTPService, private mailSvc: MailService, ) {} @Cron('0 0 * * *', { name: 'sku-discount-daily' }) async runDailyDiscountUpload() { this.logger.log('Starting SKU discount FTP upload'); try { const csv = await this.skuDiscountSvc.generateCSV(); await this.sftpSvc.upload(csv, '/remote/path/discount.csv'); await this.mailSvc.sendCronSuccess('sku-discount-daily'); } catch (err) { await this.mailSvc.sendCronAlert('sku-discount-daily', err); } } } | Linux crontab PHP script → NestJS @Cron decorator. Wrapped in try/catch with email alerting on failure. Use Bull queue for critical jobs to survive restarts. | sku_discount_generation_ftp_upload_daily.php
Multi-step Form State (Session) | // PHP Session stores multi-step form state: $_SESSION['session_content'] = array_merge( $_SESSION['session_content'], $_POST); $sku_counter = $_SESSION['session_content']['sku_counter']; $customer_code = $_SESSION['session_content']['customer_code']; | // Next.js: React Hook Form + localStorage or server draft // approach 1: localStorage draft function useOfferDraft(offerId: string) { const [draft, setDraft] = useLocalStorage( `offer_draft_${offerId}`, {} ); return { draft, setDraft }; } // approach 2: save draft to DB via API // PATCH /offers/:id/draft → OfferService.saveDraft(id, dto) // Retrieve on next step: GET /offers/:id/draft // React Hook Form with stepper: const methods = useForm<CreateOfferDto>({ defaultValues: draftData, resolver: zodResolver(createOfferSchema), }); | PHP session-based multi-step form → React Hook Form with either localStorage draft or server-side draft API. Server draft preferred for reliability. | create_offer_s1/s2/s3.php, save_offer.php